## Dark
PROJECT TITLE
Capstone Group 6 |  |  |  |  | Legend: | On track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk
Mikayla McGraw & Paige Branam
Project Start Date: | 2021-09-05 |  |  |  |  | September | [27 empty] | October
Scrolling Increment: | 0 | time axis 2021-09-05 to 2021-10-30
Milestone description | Category | Assigned to | Progress | Start | Days | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Create GitHub Organization | Low Risk | Mikayla | 100% | 2021-09-09 | 1
Create repository for ML Work | Low Risk | Paige | 100% | 2021-09-15 | 1
Create Design Layout for ML Model | Med Risk | Paige | 100% | 2021-09-18 | 3
Create Design Model for UI | Med Risk | Mikayla | 100% | 2021-09-18 | 2
Create repo for UI Work | Low Risk | Mikayla | 100% | 2021-09-18 | 1
Group Status Report 1 | Low Risk | Mikayla | 100% | 2021-09-20 | 1
Create Web App using Blazor | Low Risk | Mikayla | 100% | 2021-09-22 | 2
Group Status Report 2 | Low Risk | Mikayla | 100% | 2021-09-27 | 1
Org Chart | Low Risk | Mikayla & Paige | 100% | 2021-09-29 | 2
Research and learn Blazor | Goal | Mikayla | 50% | 2021-10-01
Create mock up image for homepage for UI | Low Risk | Mikayla | 100% | 2021-10-02 | 1
Group Status Report 3 | Low Risk | Paige | 100% | 2021-10-04 | 1
Create Home Page for UI | Med Risk | Mikayla | 100% | 2021-10-04 | 5
Research Data Grid Options Blazor | Med Risk | Mikayla | 100% | 2021-10-09 | 5
Create mock up image for account page UI | Low Risk | Mikayla | 100% | 2021-10-10 | 1
Group Status Report 4 | Low Risk | Mikayla | 100% | 2021-10-11 | 1
Create Account Page for UI | Med Risk | Mikayla | 100% | 2021-10-15 | 5
Group Status Report 5 | Low Risk | Paige | 100% | 2021-10-18 | 1
Research Database Options for Services | Med Risk | Mikayla | 100% | 2021-10-22 | 3
Group Status Report 6 | On Track | Mikayla | 100% | 2021-10-25 | 1
Create docker compose file for Music Service | Med Risk | Mikayla | 100% | 2021-10-28 | 2
Group Status Report 7 | On Track | Paige | 100% | 2021-11-01 | 1
Create music database SQL script | Low Risk | Mikayla | 100% | 2021-11-02 | 1
Create data schema for music | Low Risk | Mikayla | 100% | 2021-11-02 | 1
Create SQL Script to add dummy data for Music Service | Low Risk | Mikayla | 100% | 2021-11-06 | 2
Group Status Report 8 | Low Risk | Mikayla | 100% | 2021-11-08 | 1
GET All/single Music REST API endpoint | Med Risk | Mikayla | 100% | 2021-11-07 | 3
Create Music REST API endpoint | Med Risk | Mikayla | 100% | 2021-11-10 | 1
DELETE Music REST API endpoint | Med Risk | Mikayla | 100% | 2021-11-10 | 1
Add Postman tests to APIs | On Track | Mikayla | 50% | 2021-11-11 | 2
Add GitHub Actions for Music Service | On Track | Mikayla | 0% | 2021-11-11
Import Music Dummy Data into Account UI page data grid | On Track | Mikayla
Research UI testing strategy
Create Recommendation Service repository
Create ML Model |  | Paige
Create GET API to fetch data from model |  | Mikayla
Create Configuration Management Plan
Create tools & standards document
Create mock image of recommendation UI |  | Mikayla & Paige
Create UI Recommendation Page |  | Mikayla
Create requirments documentation
Update Design Models in docs repo
Create Design Model for Music Service
Create testing documentation
Document known bugs & issues
Create video going through app |  | Mikayla
Create user's manual
Create installation video |  | Mikayla
Create Installation Instructions
To add more data, Insert new rows ABOVE this one